## Sheet 1
sprint | story | task | status | start date | end date | who | goal
1 | creating repository | everybody shoud sign on in github | done | 97 | 97 | group | creating a place to share our project
|  | a person shoud creat 1repository and invite the rest members. | done | 98\1\17 | 98\1\18 | araste
| creating backlog |  | done | 98\1\18 | 98\1\20 | Taghibidgoli
| creating database | creating tables | done | 98\1\20 | 98\1\21 | Ramzi & Kasiri | create tables that includes productds,employee,sell,invoice,customer,person,order,order detail.
|  | finding the relation between tables | done | 98\1\21 | 98\1\22
|  | creating classes | done | 98\1\22 | 98\1\23
|  | finding the primary and foreign keies. | done | 98\1\23 | 98\1\23

## Sheet 2
sprint | story | task | status | start date | end date | who | goal
2 | creating sign on and sign in page | create insert function for users | is doing | 98\1\24 | 98\1\25 | araste | function for inserting users to DB(sign on).
|  | create select function for users | is doing | 98\1\25 | 98\1\26 |  | function for search (select) users from DB(sign in).
|  | creating sign in page | done | 98/1/26 | 98/1/28 | Kasiri | it has 2 textboxes for inserting username and password and a button for log in ,in our website.
|  | creating sign on page | done | 98/1/28 | 98/1/30 | Kasiri | it has a body that includes 6 textboxes for inserting username,password confrim ,E-mail address and phone number and address.

## Sheet 3
sprint | story | task | status | start date | end date | who | goal
3 | creating control page | creating pages(UI) | done | 98\2\1 | 98\2\4 | ramzi&kasiri | this page has the access that we said in backlog
|  | creating functions | done | 98\2\4 | 98\2\7 | araste&sotoode | function for delet,edit,insert for all entities

## Sheet 4
sprint | story | task | status | start date | end date | who | goal
4 | creating pages for looking for the products | creating index page | done | 98\2\7 | 98\2\9 | Taghibidgoli | menu includes Home, signin/sign on, category, orderpursuiting and contact us,backend about search box
it has a body that includes 6 last products
footer includes our motto.it situate in the button.
|  | creating more page | done | 98\2\9 | 98\2\10 | taghibidgoli | it has a name,image,price,description of products.that by clicking on more button or o product you can see.
|  | creating insert product function | done | 98\2\10 | 98\2\11 | araste&zolghadr | for inserting products in bod of index.
|  | creating search function for product | done | 98\2\11 | 98\2\12 | araste | for search textbox.
|  | creating category function for products | done | 98\2\12 | 98\2\13 | araste | for category bottom in menu

## sheet5
sprint | story | task | status | start date | end date | who | goal
5 | creating page about shopping | creating basket page | done | 98/2/14 | 98/2/16 | taghibidgoli | it has a box that includes name,image,price of products and a button for countinuing shopping that redirect you to detail of sending page
|  | creating detail of sendig | done | 98/2/17 | 98/2/18 | taghibidgoli&ramzi | it has a boxes for inserting customer's address,phone number,post number and name and another for chosing how to send and when
|  | creating page for shopping | done | 98/2/18 | 98/2/20 | taghibidgoli&ramzi | this page giving invoice number to customer
|  | creating select function of product | done | 98/2/14 | 98/2/15 | araste | this function search the customer's products for insert in basket page
|  | create insert function | done | 98/2/15 | 98/2/16 | araste | this function insert the customer's shopping in basket page.
|  | create insert function to DB | done | 98/2/16 | 98/2/17 | araste&zolghadr | this function insert the information ( customer had inserted in detail of sending page) in DB.
|  | select (search) function for invoice num | done | 98/2/18 | 98/2/19 | araste | this function select the invoice num from DB for show in shopping 3 page.
|  | insert function for invoice num | done | 98/2/19 | 98/2/20 | araste&zolghadr | this function insert invoicenumber to shopping3 page for customer.

## Sheet6
sprint | story | task | status | start date | end date | who | goal
6 | create pages for order pursuiting | create page(UI) for insert pursuitngnum( invoicenum) | done | 98/2/21 | 98/2/22 | taghibidgoli | it has a box that customer can insert his invoicenum
|  | create page(UI) for showing shopping situation | done | 98/2/22 | 98/2/23 | taghibidgoli | it has a box to show that what is the situation of customer's shopping
|  | create select(search)function for invoice num | done | 98/2/23 | 98/2/24 | araste | to serach the invoicenum and other information about it from DB.
|  | create insert function of situation of shopping | done | 98/2/24 | 98/2/25 | araste | to show the situation of shopping to customer.
| create page to contact us | create contact us page(UI) | done | 98/2/26 | 98/2/27 | taghibidgoli | it has our phone number,our channel ID and our E-mail address